## Slide 1
Day 48 of 60
FFIC Approvals on time
Project Update Dashboard – Government Approvals
Project Objective: To secure government approvals in various regions for SoliD
Project Time: 60 business days starting April 1
Project Risks:
  Resource availability out next week. May cause delays if alternate is not made available to us.
  Budget is over by $6,200. More costs may be needed next week.
Project Updates:
  FFIC Approvals are on time per the plans
  Approved documents onto Verification Office for sign off
  This week, 5 of 8 major tasks were completed. The 3 incomplete are to be completed next week along with 4 others
Next Steps:
  Seek alternative for resource constraint
  Complete the next 7 scheduled tasks by Day 53
Notes: Thank you for your attention today. I shall briefly update everyone on the status, progress, and risks on the SolID mobile app project and the SoliD Governmental Approvals project.
Starting with the Government Approvals project. This project is progressing per plans. Per the chart on this slide, 48 days in; on time delivery for FFIC approvals; approved documents onto Verification Office for sign off. This week, 5 of 7 tasks were completed. The 2 incomplete are to be completed next week along with 4 others.
Known risks are reduced resource availability for next week. Mitigation plan underway.
The budget is over by $6,200. The planned budget for next month may be insufficient. We are looking to reconcile exact areas and will update you.

## Slide 2
Iteration 4
Next Product Release: Tomorrow
Project Update Dashboard – Mobile App
Project Objective: To develop a mobile app for potential and existing customer of SoliD
Project Time: The app is iterating over many two week iterations with releases delivered regularly
Project Updates:
  Issues fixes from last release
  Positive feedback for beta testers
  With PO acceptance, next release may go out tomorrow
Project Risks:
  No known risks
Project Next Steps:
  Iteration 5 starts the day after next
  Beta testers to try out next release
  Extending the product beyond initial user base
Notes: The issues uncovered for the last release have been fixed. Feedback from our end users has been very positive. The current iteration ends today. The team will review with the Product Owner in the morning. If content is approved, the team may release another update to the app tomorrow.